## Project plan
Service ID | Sevice Name | Task | Status 1 | Status 2 | Final Report | Agent
S1 | Ski Resort | Find dataset | Done | - | - | Wayne | V2 | Report 2 Update
|  | Data upload to database | In Progress | Done | -
|  | Create DAO classes | Not started | Done | -
|  | Create SVC class(es) | Not started | Done | -
|  | Create Controller class |  | Done | -
|  | Perform Testing |  | In progress | Done
S2 | Restaurants | Find dataset | Done | - | - | Matthew
|  | Data upload to database | In progress | Done | -
|  | Create DAO classes | Not started | Done | -
|  | Create SVC class(es) | Not started | Done | -
|  | Create Controller class |  | In progress | Done
|  | Perform Testing |  | Not Started | Done
S3 | Museums | Find dataset | Done | - | -
|  | Data upload to database | In progress | Done | -
|  | Create DAO classes | Not started | Done | -
|  | Create SVC class(es) | Not started | Done | -
|  | Create Controller class |  | Done | -
|  | Perform Testing |  | In progress | Done
S4 | Software companies | Find dataset | Done | - | - | Vatsal
|  | Create node.js project | Done | - | -
|  | Connect database and link with Bluemix | In progress | Done | -
|  | Find deatils from database and return a response to it | Done | - | -
|  | Create bluemix node js server | Done | - | -
|  | Add mongodb (mLab) connection | - | Done | -
|  | Add api endpoint for customise search functionality | - | In Progress | Done
|  | Deployment on Bluemix server and create endpoint of a service | - | Done | -
S5 | GUI (Graphical User Interface) | Initialize react app | Done | - | - | Gary
|  | Connect react app with Bluemix | In progress | - | Done
|  | Implement dashboard with search functionality for services | In progress | - | Done
|  | Implement results screen for each service | - | - | Done
|  | Create registration and login page | - | In Progress | Done
|  | Implement results screen | - | In Progress | Done
S6 | Registry and Discovery | Initialize Eureka Server | Done | - | - | Chengyuan
|  | Initialize Eureka Clients | In progress | Done | -
|  | Enable Springcloud Gateway | Done | - | -
|  | Enable RESTful API UI (Swagger) | In progress | Done | -
|  | Enable Feign | Not Started | Done | -
S7 | Authentication Service | Create table for a user | - | Done | - | Vatsal
|  | Connection with database | - | Done | -
|  | Verify a user with POST event of login API | - | Done | -
|  | Verify a user when a new request arrive on a server | - | Done | -
|  | Create a token using JWT and store | - | Done | -
|  | Deployment of a service on IBM | - | Done | -
|  | Verify and return response to gateway | - | Done | -
|  | In Testing & Deployment | - | In Progress | Done
S8 | Gateway Service | Create gateway (nodejs service) on IBM bluemix | - | Done | - | Vatsal
|  | Add endpoint of all microservices to access it | - | Done | -
|  | Create an endpoint for a client to access list and search | - | Done | -
|  | Create a endpoint to access live services from a registry | - | Done | -
|  | Authentication process of a user | - | Done | -