## Project plan
Service ID | Sevice Name | Task | Status | Agent
S1 | Ski Resort | Find dataset | Done | Wayne
|  | Data upload to database | In Progress
|  | Create DAO classes | Not started
|  | Create SVC class(es) | Not started
S2 | Restaurants | Find dataset | Done | Matthew
|  | Data upload to database | In progress
|  | Create DAO classes | Not started
|  | Create SVC class(es) | Not started
S3 | Museums | Find dataset | Done
|  | Data upload to database | In progress
|  | Create DAO classes | Not started
|  | Create SVC class(es) | Not started
S4 | Fortune 500 companies | Find dataset | Done | Vatsal
|  | Create node.js project | Done
|  | Connect database and link with Bluemix | In progress
|  | Find deatils from database and return a response to it | Done
|  | Create bluemix node js server | Done
S5 | GUI (Graphical User Interface) | Initialize react app | Done | Gary
|  | Connect react app with Bluemix | In progress
|  | Implement search functionality for services | In progress
|  | Implement results screen for each service | Not Started
S6 | Non-Service: Microservice Configuration | Initialize Eureka Server | Completed | Chengyuan
|  | Initialize Eureka Clients | In progress
|  | Enable Springcloud Gateway | Completed
|  | Enable RESTful API UI (Swagger) | In progress
|  | Enable Feign | Not Started